## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Ben | 9400 | 300 | 9100 | 4400 | 0 | 4400 | 1000 | 300 | 700 | 1000 | 0 | 1000 | 3000 | 0 | 3000
Brent | 8700 | 6050 | 2650 | 3700 | 600 | 3100 | 1000 | 350 | 650 | 1000 | 1100 | -100 | 3000 | 4000 | -1000
Caleb | 10300 | 300 | 10000 | 5300 | 0 | 5300 | 1000 | 300 | 700 | 1000 | 0 | 1000 | 3000 | 0 | 3000
Claire | 9600 | 400 | 9200 | 4600 | 0 | 4600 | 1000 | 300 | 700 | 1000 | 100 | 900 | 3000 | 0 | 3000
Damien | 8600 | 350 | 8250 | 3600 | 0 | 3600 | 1000 | 350 | 650 | 1000 | 0 | 1000 | 3000 | 0 | 3000
Gibby | 9600 | 300 | 9300 | 4600 | 0 | 4600 | 1000 | 300 | 700 | 1000 | 0 | 1000 | 3000 | 0 | 3000
Shashwot | 9100 | 1500 | 7600 | 4100 | 0 | 4100 | 1000 | 300 | 700 | 1000 | 1200 | -200 | 3000 | 0 | 3000
Total | 65300 | 9200 | 56100 | 30300 | 600 | 29700 | 7000 | 2200 | 4800 | 7000 | 2400 | 4600 | 21000 | 4000 | 17000

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Ben |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Title screen | 6 |  | planned | key 1: planned; complete 2: planned; this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned
Pause menu | 4 |  | planned | planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned
Unit tooltip (On hover) | 2 |  | planned | planned 11: planned; planned 12: planned
Unit stats element | 6 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned
Win screen | 4 |  | planned | planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned
Lose screen | 4 |  | planned | planned 23: planned; planned 24: planned; planned 25: planned; planned 26: planned
Help menu | 4 |  | planned | planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned
Settings menu | 8 |  | planned | planned 31: planned; planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned; planned 37: planned; planned 38: planned
Text boxes that can pop up | 2 |  | planned | planned 39: planned; planned 40: planned
Combat prediction | 4 |  | planned | planned 41: planned; planned 42: planned; planned 43: planned; planned 44: planned
totals | 44 | 0
Brent
Get Attributes | 2 | 1 | planned | key 1: planned; complete 2: planned
Determine enemy in range for event | 8 |  | planned | this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned
Select event | 8 | 2 | planned | planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned
Calculate damage | 5 | 2 | planned | planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned
Update health | 2 | 1 | planned | planned 24: planned; planned 25: planned
Eliminate units | 2 |  | planned | planned 26: planned; planned 27: planned
Animate death | 5 |  | planned | planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned
Animate battle | 5 |  | planned | planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned; planned 37: planned
totals | 37 | 6
Caleb
Grid class | 2 |  | planned | key 1: planned; complete 2: planned
Player input for moving the cursor | 2 |  | planned | this week 3: planned; planned 4: planned
Cursor movement and animation | 5 |  | planned | planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned
Movement calculation | 4 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned
Unit range | 6 |  | planned | planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned
Enemy range display | 6 |  | planned | planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned; planned 25: planned
Turns | 6 |  | planned | planned 26: planned; planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned
Overworld between maps | 8 |  | planned | planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned; planned 37: planned; planned 38: planned; planned 39: planned
Fog of war | 10 |  | planned | planned 40: planned; planned 41: planned; planned 42: planned; planned 43: planned; planned 44: planned; planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
Sounds are altogether | 4 |  | planned | planned 50: planned; planned 51: planned; planned 52: planned; planned 53: planned
totals | 53 | 0
Claire
Level plan 1 | 3 |  | planned | key 1: planned; complete 2: planned; this week 3: planned
Level plan 2 | 3 |  | planned | planned 4: planned; planned 5: planned; planned 6: planned
Level plan 3 | 3 |  | planned | planned 7: planned; planned 8: planned; planned 9: planned
Level plan 4 | 3 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned
Tutorial plan | 3 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned
Player spawning | 1 |  | planned | planned 16: planned
Tile spawning | 3 |  | planned | planned 17: planned; planned 18: planned; planned 19: planned
Enemy spawning | 2 |  | planned | planned 20: planned; planned 21: planned
Level complete | 2 |  | planned | planned 22: planned; planned 23: planned
Implement level 1 | 3 |  | planned | planned 24: planned; planned 25: planned; planned 26: planned
Implement level 2 | 3 |  | planned | planned 27: planned; planned 28: planned; planned 29: planned
Implement level 3 | 3 |  | planned | planned 30: planned; planned 31: planned; planned 32: planned
Implement level 4 | 3 |  | planned | planned 33: planned; planned 34: planned; planned 35: planned
Implement tutorial | 4 |  | planned | planned 36: planned; planned 37: planned; planned 38: planned; planned 39: planned
Level balancing | 5 |  | planned | planned 40: planned; planned 41: planned; planned 42: planned; planned 43: planned; planned 44: planned
Level art | 2 |  | planned | planned 45: planned; planned 46: planned
totals | 46 | 0
Damien
Pathfinding (location, "vision", distance from player unit, etc.) | 7 |  | planned | key 1: planned; complete 2: planned; this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned
Interaction with tiles | 5 |  | planned | planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned
Envoke attacking the player | 2 |  | planned | planned 13: planned; planned 14: planned
Special AI "general setup" | 2 |  | planned | planned 15: planned; planned 16: planned
Boss AI | 3 |  | planned | planned 17: planned; planned 18: planned; planned 19: planned
Need to heal knowledge | 3 |  | planned | planned 20: planned; planned 21: planned; planned 22: planned
Special movement patterns | 4 |  | planned | planned 23: planned; planned 24: planned; planned 25: planned; planned 26: planned
Won't attack if it won't hit | 3 |  | planned | planned 27: planned; planned 28: planned; planned 29: planned
Inventory decisions | 3 |  | planned | planned 30: planned; planned 31: planned; planned 32: planned
Special interactions, recruitable | 4 |  | planned | planned 33: planned; planned 34: planned; planned 35: planned; planned 36: planned
totals | 36 | 0
Gibby
Classes - 5 or so? | 8 |  | planned | key 1: planned; complete 2: planned; this week 3: planned; planned 4: planned; planned 5: planned
Health | 3 |  | planned | planned 6: planned
Speed/Movement Restrictions | 5 |  | planned | planned 7: planned; planned 8: planned
Attacks | 8 |  | planned | planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned
Damage Values | 2 |  | planned | planned 16: planned
Dr. BC mode and trigger | 2 |  | planned | planned 19: planned
Unit Sprites | 4 |  | planned | planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned
Unit Animation | 4 |  | planned | planned 24: planned; planned 25: planned; planned 26: planned; planned 27: planned
Luck/Dodge Chance/Crit | 2 |  | planned | planned 28: planned; planned 29: planned
Player/enemy distinction | 2 |  | planned | planned 38: planned
Base Class | 4 |  | planned | bar: planned 30 to planned 33
Attack Range | 2 |  | planned | planned 39: planned
totals | 46 | 0
Shashwot
Dimension | 2 |  | planned | key 1: planned; complete 2: planned
Art and design - UI | 4 |  | planned | this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned
Dimension Detection | 2 |  | planned | planned 7: planned; planned 8: planned
Events | 4 |  | planned | planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned
Object Tiles | 4 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned
Collision Tiles | 4 |  | planned | planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned
Trap Tiles | 4 |  | planned | planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned
Teleportation Tiles | 4 |  | planned | planned 25: planned; planned 26: planned; planned 27: planned; planned 28: planned
Healing Tiles | 4 |  | planned | planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned
Time Effect | 3 |  | planned | planned 33: planned; planned 34: planned; planned 35: planned
Doors (Access from keys) | 3 |  | planned | planned 36: planned; planned 37: planned; planned 38: planned
Treasure tiles | 3 |  | planned | planned 39: planned; planned 40: planned; planned 41: planned
totals | 41 | 0
group totals (hrs) | 303 | 6
group totals ($) | 30300 | 600

## Meetings
| Date | Aug. 29 | Sept. 4 | Sept. 10 | Oct. 18
| Purpose | First Meeting | Task Assignments | Task Breakdowns | Testing
| Hours | 1 | 1 | 1 | 0.5
Ben | 3 | ü | ü | ü
Brent | 3.5 | ü | ü | ü | ü
Caleb | 3 | ü | ü | ü
Claire | 3 | ü | ü | ü
Damien | 3.5 | ü | ü | ü | ü
Gibby | 3 | ü | ü | ü
Sashwot | 3 | ü | ü | ü
Total | 19 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Ben | Individual schedule | 2
| Champion | 5
| RFP - Section 4, Glossary Terms | 3
| Subtotal | 10 | 0
Brent | Individual schedule | 2 | 2
| Champion | 5 | 5
| RFP - Editor | 3 | 4
| Subtotal | 10 | 11
Caleb | Individual schedule | 2
| Champion | 5
| RFP - Section 1 and 3, Glossary Terms | 3
| Subtotal | 10 | 0
Claire | Individual schedule | 2 | 1 | bar: 1
| Champion | 5
| RFP - Section 7 and 9, Glossary Terms | 3
| Subtotal | 10 | 1
Damien | Individual schedule | 2
| Champion | 5
| RFP - Section 5 and 6, Glossary Terms | 3
| Subtotal | 10 | 0
Gibby | Individual schedule | 2
| Champion | 5
| RFP - Section 2, Glossary Terms | 3
| Subtotal | 10 | 0
Shashwot | Individual schedule | 2
| Champion | 5
| RFP - Section 8, Glossary Terms | 3
| Subtotal | 10 | 0
| Total | 40 | 12
red is dependent on others

## Overhead
| Ben | Brent | Caleb | Claire | Damien | Gibby | Shashwot
Training |  | 20
SA Presentation Prep
Software Specialist Presentation Prep
Team Lead Presentation Prep |  | 20
Oral Exam Prep
Post Mortum Presentation Prep
Total | 0 | 40 | 0 | 0 | 0 | 0 | 0